ASSIGNMENT 6

1. How do you evaluate the performance of a project in agile?

We can evaluate the performance of a project in agile by considering several factors such as velocity, hit rate, work remaining on task, project cost etc
Here the term velocity refers to the number of storypoints that can be taken in a sprint, if the velocity of the project is higher than than we expected then it means the project is on track.
- Cost Performance Index (CPI), Schedule Performance Index (SPI), Earned Business Value (EBV) are the other techniques used to evaluate the performance.
- Earned Business value can be used to measured technical performance, cost and schedule against planned performance within a given project. It helps to measure technical performance, schedule and actual cost to provide metrics for work actually accomplished. By comparing the earned value (EV) with the planned value (PV) the actual progress on the project is compared against the expected progress which yields valuable information.
- The Schedule Performance Index indicates how efficiently the team is progressing compared to the planned progress.
- The Cost Performance Index helps to calculate the the cost utilized by the project. It measures the value of the work completed compared to the actual cost spent on the project.

2. Compare traditional monitoring & control with agile monitoring & control with respect to metrics generation

Traditional monitoring & control	Agile monitoring & control
It is difficult to accurately estimate costs for any software development project. The actual performance of a project cannot be estimated easily	Technical performance, schedule and actual cost can be estimated by comparing the earned value (EV) with the planned value (PV)
Business value is not determined	EBV is used to calculate business value
Monitoring and control will only occur in last phase of the project.	Here the monitoring and control will be happen in each sprint release.
Effort is calculated only at the last phase of the project.	Effort is calculated on each sprint.
Quality is measured in only one phase in the whole project life.	Quality is measured in each sprint life cylcle.
Risk matric is calculated for finding the open,closed risks associated with the project for the whole life.	Here risk will be checked for each sprint release.

3. With a total project budget of $ 175,000, and having completed one out of four Iterations, we have this product backlog and these actuals:

Feature	Estimate (storypoints)	Completed(storypoints)	Actual Cost(1000s / dollars)
Welcome Screen	10	10	15
Advert - Splash Screen	20	20	30
Login Screen	10	10	20
Personalized Google Ads	20
Catalog Browser	20
Catalog Editor	10
Shopping Basket Browser	5
Shopping Card Editor	25
Check-out Process	20
Invoice Calculation	10
Credit Card Verification	10
PayPal Payment Handling	20
Order Confirmation Email	20
Totals	200	40	65

In our example, after Iteration 1 we should be at 25% complete)
- Calculate Planned Value
- Actual % Complete
- Earned Value

Answer:
planned Value =(25/100) * 175,000 = $ 43,750
Actual % Complete= (40/200)*100= 20%
Earned Value= (20/100)*175,000= $35,000